## Utilization
Utilization in November | [7 empty] | Total Hours: 166 | [5 empty] | Utilization in December
Name | Roles and Responsibilites | Utilization in % for project | Utilization in % for Training | Skills to develop | Week1 | Deliverables | Week2 | Deliverables | Week3 | Deliverables | Week4 | Week4 Deliverables |  | Week1 Tasks | Deliverables | Week2 Tasks | Deliverables
D.Bala Ramya | 1.Try to find the algorithms for face recognition and face detection. 2.DataBase for Maintaining Data. 3.GUI for user interaction 4.Identifying and analyzing various face detection patterns/algorithms 5.Developing Image processing applications like Motion Tracking and Augmented Reality 6.Written testcases & test Scripts 7.Followed Votary Tech VGate process in SDLC as per CMMi 3. | OpenCV: Haar algorithm-70% LBPH Algorithm-60% Designing GUI-90% Git-80% Database-50% | Shell Scripting-100% | OpenCV,Python Tkinter,Camera Driver | 1.Design Document updation. 2.Development Dependency Document updation. 3.Reviewing SRS Document. 4.Reviewig Testcases Document. | 1.All Documents updated and Designed as per the requirement. | 1.Identification of face Detection Alogorithms in OpenCV. 2.Developing Application To recognise face. | 1.Identified LBPH Algorithm and API’s To recognise Face. 2.Checked Haar and LBPH API’s | 1.Using LBPH ApI’s to recognise Face. 2.Understanding Opencv API’s. 3.Wrapper Implementation. 4.API’s Design and Implementation. | 1.Recognise face for a trained person. 2.Tried to implement wrapper. | 1.Attended Shell Scripting Training. 2.GUI Design for User interacton In python. 3.Wrapper Design Document Updation. | 1.Attended Shell Scripting Training. 2.GUI Design for User interacton In python. 3.Wrapper design document updation. 4.Filled the Templates as per the V-Gate Process. |  | 1.Understanding About Yocto. 2.Generate U-boot Image and flash It on Dragon Board. 3.Generate images for Dragon Board Using Yocto. 4.Prepare Documentation for U-boot Flashing. | 1.Understand about Yocto. 2.Load u-boot Image for dragon Board. 3.Board bring up for Dragon Board using Yocto. 4.Attended interview in Qualcomm | 1.Write a shell script to i)To select a board dynamically. ii).Add Packages dynamically using Yocto iii) Add Driver modules dynamically using Yocto. | 1.Added packages and tools like .. vim,python,gcc,git for dragon board dynamically using Yocto. 2.Written a shell script to select board dynamically,to add packages dynamically, add tools dynamically using Yocto. 3.Tested that script with dragon board. 4.Written Test cases for stagefright. 5.Written a document for Dragon Board bring up,adding packages for Dragon Board using Yocto.
Name | Week 1 | Deliverables | Week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 5 | Deliverables |  | Week 1 | Deliverables | Week 2 | Deliverables
Dayanand Patil | 1)Understanding Project Requirements. 2)Understanding Open CV module. 3)Installation of OpenCV module. | Understood Open Cv | 1)Analyzed the GUI Module. 2)Prepared SRS and Use Case document. 3)Understanding Image Processing concepts | SRS and UseCase Document | 1)Tested GUI Module. 2)Worked on Face detection Module. 3)Attended Multimedia Trainig. 4)Worked on Audio Codecs Extraction. | 1)Types of Audio & Vedio Codecs. 2)Collected Parser data for MP3 File. 3)Test Cases for MP3 Audio File. | 1)Written Test Cases for GUI. 2)Written Camera Testcase. 3)Attended Shell Scripting Trainig. | Camera Testcase document. | 1)Attended the XML & DBMS Trainig. 2)Analysing the Automatuion Feasibility for OpenCV project. | Basics of XML & DBMS |  | 1)Understanding Yocto build process. 2)Understanding Uboot. 3)Generated uboot image for target board(Beaglebone board). 4)Generated image for bring up target board(Beaglebone board) using yocto. | Successfully generated images and flashed on target board. | 1)Understanding the Stagefright framework. 2)Understanding the audio flow in android Stagefright . 2)Written Test Cases for same. 3)Created the dashboard using python. 4.Written shell script to automate the yocto build process. | 1.Test cases document. 2.Dashboard. 3.Automated Yocto build process.
Name | Roles and Responsibilites | Utilization in % for project | Utilization in % for Training | Skills to develop |  | Week1 Deliverables |  | Week2 Deliverables |  | Week3 Deliverables |  | Week4 Deliverables | Week1 Tasks | Deliverables | Week2 Tasks | Deliverables
P.Deepika | 1.Try to find the algorithms for face recognition and face detection. 2.DataBase for Maintaining Data. 3.GUI for user interaction 4.Identifying and analyzing various face detection patterns/algorithms 5.Developing Image processing applications like Motion Tracking and Augmented Reality 6.Written testcases & test Scripts 7.Followed Votary Tech VGate process in SDLC as per CMMi 3. | OpenCV: Haar algorithm-60% LBPH Algorithm-60% Designing GUI-60% Git-80% Database-50% | Shell Scripting-100% | OpenCV,Python Tkinter,Camera Driver | Identifaction OpenCV Algorithms For face detection. | 1.Design Document updation. 2.Development Dependency Document updation. 3.Reviewing SRS Document. 4.Reviewig Testcases Document. 5.Studied about OpenCV | Try to give input and checking Output for Haar Algorithm. | 1.Identification of face Detection Alogorithms in OpenCV. 2.Developing Application To recognise face. | Try to give input and checking Output for LBPH Algorithm. | 1.Using LBPH ApI’s to recognise Face. 2.Understanding Opencv API’s. 3.API’s Design and Implementation. 4.Design Document updation with Algorithms. | Wrapper Integartion with Application. | 1.Attended Shell Scripting Training. 2.Design Document updation. | 1.Understanding About Yocto. 2. U-boot configuration and compilation and flashing image on Beaglebone black Board. 3.Generate images for Raspberripi3 and Dragon Board Using Yocto. 4.Understanding the stagefright framwork. | 1.Understand about Yocto. 2.Flashing u-boot Image on beaglebone black Board. 3.Building images for Raspberripi3 and Dragon Board using Yocto. 4.Attended interview in Qualcomm | 1.Understanding the stagefright framwork. 2.Reading about how to add own plugins using OpenMax in stagefright player. 3.Compiling source code for Raspberripi3 and Dragon Board Using Yocto. | 1.Prepare a documentation about Stagefright. 2.Reading about how to add own plugins using OpenMax in stagefright player. 3.Flashing images for Raspberripi3 and Dragon Board Using Yocto. 4.Learn how to add a packages and tools like .. vim,python,gcc,git for Raspberripi3 board statically using Yocto.

## Dev Project Plan
4A Camera Project Plan
|  |  | October | [7 empty] | November | [7 empty] | December
|  |  | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables
| WBS | Enginners Assigned: 11 Haranath Murali Dama Jignesh N Patel Divya Preethika ShashankArora Rakesh Bathini Yasir NL Swetha Huded Satheesh Pradeep Gopinath Shaikh Ishaque Mallikarjun | 1)Camera driver for RPI3. 2)Undestanding ISP | Camera Driver | 1)Understanding camera drivers 2)Understanding v4l2 driver | V4l2 Driver | 1)Understanding of V4L2 2)Understanding of ALSA | V4L2 & ALSA | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app 3)LTP testing | Camera Feature, Gstreamer Test Suite | 1)Understanding Bringing up of Dragon board & Porting and integration | Understanding of Bringing up of Dragon board | 1)Bringing up of Dragon board 2)Porting and integration | Bringing up of Dragon board | 1)Understanding of gstreamer from hardware to application (use linux apps or write Android app) 2)Yocto Skills | Gstreamer & Yocto Skills | 1)Changing v4l2 reflashing using YOCTO 2)Changing ALSA reflashing using YOCTO | Changing V4L2 & ALSA through Yocto | 1)Understanding of HAL | Android HAL Understanding | 1)Customizing HAL in RP3 and reflashing using YOCTO | Customizing HAL in RP3 and reflashing using YOCTO | 1)LTP testing 2)Customizing dragon board HAL – V4l2 | Dragon board HAL – V4l2 | Customizing dragon board HAL – ALSA | HAL-ALSA On Dragonboard
| task 1 | 1)Understanding of Camera driver for RPI3. 2)Undestanding ISP
| task 2 | 1)Understanding of Camera driver for RPI3. 2)Understanding of V4L2 driver
| task 3 | 1)Understanding of V4L2 for RPI3. 2)Understanding of ALSA driver
| task 4 | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app
| task 5 | LTP testing
Delivery | task 6 | Camera Feature, Gstreamer Test Suite
| task 7 | 1)Understanding of Dragon Board 2)Understanding of Board Bring Up Dragon Board
| task 8 | Understanding of gstreamer from hardware to application (use linux apps or write Android app)
Delivery | task 9 | Yocto Skills
| task 10 | Changing v4l2 reflashing using YOCTO
| task 11 | Changing ALSA reflashing using YOCTO
| task 12 | Android porting on RPI3
Delivery | task 13 | Understanding of Android HAL
| task 14 | Customizing HAL in RP3 and reflashing using YOCTO
| task 15 | LTP testing
| task 16 | Customizing dragon board HAL – V4l2
| task 17 | Customizing dragon board HAL – ALSA
Android Audio Processing Project
|  | Ashok L Mohd Pasha Shravya Kumbham Smruthi Ranjan | BSP of RP3 | Board Bring up | Build kernerl using Yocto | YOCTO training | BT audio integration with RP3 | GIT /Gerit | BT audio Integration | BT audio Integration | Understand gstreamer | Audio codec Test scripts | Integrate gstreamer on linux machine | gstreamer | Tracing the HAL | Porting on Intel | understand ALSA | gstremer plugins | Building with changes to ALSA |  | DSP Noise cancellation algorithms analysis | Small PoC with DSP Algorithms | Making changes to DSP and buiding |  | Fixing bugs | DSP modified Audio processing demo
[7 empty] | Playing BT audio over RP3 | Jenkins configurations | Integration testing | Python test scipts | study DSP |  | Testing BT audio with gsteamer | BT audio playing on gstremer | Understand kernel | Integrate gstremer on linux | Tracing the flow from ALSA to drivers |  | DSP noise cancellation algorithm study |  | Implementing noise cancellation algorithm | preparing Test plans | bug fixing | Limited working demo playing BT audio with changes to DSP | comparison testing of audio
[7 empty] | Submissions using GIT / Gerrit |  |  |  | preparing test data |  | Bug fixes |  | Porting on other boards | Android framerwork | making changes in the gstreamer plugins and writing new gstreamer plugins | [5 empty] | writing test scripts |  | cancellation of particular noise filter
[7 empty] | study Android framework | Android framework |  |  |  |  | playing BT audio with gstreamer |  | Integrate gstreamer on RP3 | [7 empty] | pyton automation
[13 empty] | Playing audio files |  | Integrate with Android
Open CV/CL Image processing Project
|  | Ashok Siva Kumar Ramya Bala Anjaneyulu Deepika Rathod Raja Vithal Sandeep Goud Sandeep Reddy | BSP of RP3 | Board Bring up | Build kernerl using Yocto | YOCTO training | I2c Writing camera driver | GIT /Gerit | Application and Driver Integration | BT audio Integration | Integrating Python image processing libraries to development environment | Running the image to detect and recognize face demo | Integrating EMGU CV | Detecting the geometric shapes | Implementing the photometric stereo algorithm | Testing face. Geometric and photometric relationship | Creating new c++ libraries (if possible) | Modular code libraries for c++ | Integrating the opencv/cl onto RP3 | prodcutise the code for demo over RP3 | Integrating the code onto client board
[7 empty] | Integrating camera to RP3 | Jenkins configurations | Taking picture, fixing bugs | Camera related Python scripts | Study of various Image processing libraries | writing test scripts | Detecting face for Geometric relationship algorithm | Connectivity to database | Running the python scripts and testing combination of Input Image / Face detection |  | creating new python packages | Modular code libraries for python | running the algorithms from conencted camera
[7 empty] | Submissions using GIT / Gerrit | Camera Driver testing | Modifying the Driver |  | Creating Face detection algorithm |  | Running test cases accordingly |  | using the existing algorithms to process and train the pictures
[7 empty] | study Android framework |  | Writing Test scripts |  | writing python extraction libraries |  | connectivity to data base MangoDB over cloud
[7 empty] | Camera Driver Testing |  | creating python scripts for the https://cloud.google.com/vision/ APIs integrate | createing environment setup | creating a GUI /UX in Django to process image |  | training algorithm to detect and process the pictures
[7 empty] | Study open cv algorithms | [5 empty] | storing the processed pictures with metadata for comparitive retrieval

## SkillsRating
| Haranath | Murali | Jignesh | Mallikarjun | Sateesh | Rakesh | Divya | Shashank | Swetha | Isaque | Yasir
Board bring up (RP3) | 8 | 5 | 8 | 8 | 6 | 6 | 7 | 8 | 8 | 7 | 7
YOCTO | 6 | 3 | 6 | 6 | 4 | 5 | 5 | 5 | 3 | 4 | 7
Integration of BT with RP3 | 8 | 6 | 6 | 8 | 5 | 4 | 4 | 6 | 7 | 3 | 6
Debugging and fixing BT issues | 7 | 4 | 7 | 7 | 6 | 4 | 5 | 6 | 7 | 3 | 4
Integration of gstreamer | 4 | 2 | 4 | 4 | 3 | 8 | 7 | 3 | 8 | 4 | 6
BT audio using gstreamer | 4 | 2 | 5 | 4 | 3 | 6 | 5 | 3 | 6 | 4 | 4
Gerrit server | 8 | 8 | 7 | 6 | 9 | 7 | 8 | 3 | 5 | 7 | 7
Scons | 2 | 7 | 0 | 3 | 3 | 5 | 7 | 3 | 3 | 7 | 6
Build and Integration | 5 | 8 | 4 | 5 | 7 | 7 | 8 | 5 | 4 | 7 | 6
Python scripts | 6 | 2 | 1 | 5 | 5 | 4 | 5 | 2 | 4 | 6 | 5
UDP streaming for wifi | 5 | 1 | 2 | 3 | 3 | 3 | 3 | 4 | 7 | 0 | 0
LTP testing | 4 | 0 | 4 | 4 | 4 | 4 | 1 | 4 | 1 | 2 | 4
Device drivers | 8 | 5 | 7 | 8 | 4 | 3 | 2 | 7 | 5 | 3 | 5
Test and bug fixing | 7 | 5 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 6
Open source submission | NA | 5 | NA | NA | NA | 7 | NA |  | NA | NA | NA