## January_Sheet
Project name :Implementing custom Gstreamer plugin for media streaming
Utilization in January-2018 | [10 empty] | Utilisation in Feburary-2018
S. No. | Name | Roles and Responsibilites | Week1 | Deliverables | Week2 | Week2 Deliverables | Week3 | Deliverables | Week4 | Deliverables | Week1 | Deliverables | Week2 | Deliverables | Week3 | Deliverables | Week4 | Deliverables
1 | Sandeep Reddy | 1.Uderstanding gstreamer on android 2.Installatin of gstreamer on android 3.integrating gstreamer with android 4.writing audio plugin for android 5.writing plugin to capture image and encode it into differrent formates 6.creating application which plays audio and video file in android 7.Adding apk file to android source code | 1.understanding of gstremer in android 2.Installatin of gstreamer on for android | 1.understanding of gstremer in android 2.Installatin of gstreamer on for android | 1)Customising gstreamer plugin in android for media streaming using android studio. 2)Created application to play default audio test file on android and tested on rpi | Audio streaming using gstreamer on android. | 1.created application to play local audio and video file on android. 2.tryied to port gstreamer on android using cerbero | Application which plays local media file. | 1.Adding APK to the android source code 2.implement playback service in binder ipc in hal | playback service in binder ipc on android | 1.Understanding of Display and graphics | Understanging of Display | 1.developed an application To change the video playback Speed | 1.app which changes playback speed dynamically | 1.developed an app to change The brightness, color, contrast And tested on dragon board | 1.app which changes the Brightness,color,contrast | 1.need to develop an app To change the framerate
2 | Ramya D | 1.Build bellagio on linux machine 2.Play an audio file using that bellagio. 3.Understnding of Gstreamer. 4.Port android 6.0 into dragon board. 5.Build Gstremer. 6.Integrate gstreamer with android source code | - | - | 1.Understanding about Gstreamer. 2.Integrate Gstreamer with android source code. | Understanding of Gstreamer. Trying to build android. | 1.Android build is completed and flashed that images into Dragon Board. 2.Gstreamer build is completed using cerbero. | 1.Build & Flashed the Android images on dragon board 2. Build gstreamer using cerbero. | 1.Add APK file to android source code and build. 2.Implement playback service in binder ipc in HAL. | Trying to add apk file to android source code. | 1.Understanding of Display and graphics | Understanging of Display | Implement a gstreamer plugin | Myfilter element is generated | 1.developed an app to change The brightness, color, contrast And tested on dragon board. 2.Attended Interview 3.Building linux image for Dragon board. | 1.Developed an app to change the Brightness,contrast,hue,saturation of a video. | 1.Write a gstreamer Application to change the frame rate of a video
3 | Rahul Chaturvedi | 1) Understanding of gstreamer on android. 2) Build Android images for dragon board . 3) Written Use case document. 4) Written Test cases. 5) Written scripts for same. 6. Developed the dashboard for test report | 1)Analyzed the test cases for feasibility of automation. 2)Enhance the TestCases. 3)Written a batch file for Automate the test sripts. | 1.Dashboard for test report. 2.Batch file for automate the scrpts. | 1. Modify the test cases. 2. written the scripts for same . 3. Tried to build the android image for dragon board but getting java version issue. | 1.Test scripts for gstreamer 2.android build for Dragonboard | 1. Written the use case for gstreamer plugin. 2.Enhance the Test cases. 3. Generated Android images for dragon board & flashed that images into dragon board. | 1.Use case document. 2.Build & Flashed the Android images on dragon board | 1.Enhance the Number of Test Cases. 2. Understanding GITHUB. 3. CI through GITLAB. | 1.Understood GITLAB 2. Test Cases. | 1)Analyzed the test cases for feasibility of automation. 2)Enhance the TestCases. 3)Written a batch file for Automate the test sripts. | 1.Dashboard for test report. 2.Batch file for automate the scripts. | 1. Modify the test cases. 2. written the scripts for same . 3. flashed android images into dragon board. | 1.Test scripts for gstreamer 2.Successfully flashed image and bringup the board. | 1. Written the test cases for display setting through gstreamer plugin. 2.Automated test cases for the same. | 1.Test case document. 2.Automation scripts for display setting
4 | Swetha Huded | - | - | - | - | - | - | - | - | - | Attended Interview Qualcomm Banglore |  | Interview Preparation |  | 1.Interview Preparation 2.Understanding Makefiles 3.Exploring about how to create gst element 4.Makefiles Understanding 5.Creating plugin for varying brightness | Gstreamer application to change framerates at runtime | 1.Rampup of Kernel and Device Driver Implementing Gst-element 2.Preparing c and Linux Questions | Need to create unique gst-element
5 | Puspalatha | 1) Creation of test designs, test processes, test cases and test data. 2) Carry out testing as per the defined procedures . | - | - | - | - | - | - | - | - | 1)Understood the procedure of testing. 2)Analyzed the test cases for manual. | 1)Understood how to write the testcases. | 1.Enhance the TestCase. 2. Tried to write some test cases on Gstreamer. | 1.written some testcases on Gstreamer. | 1. Tested the playing of Audio&Video by using Gstreamer. 2.tested the display by using Gstreamer. | 1. Written some test cases on playing Audio&Video by using Gstreamer.