## Sheet1
IOT Based Alert System to Highlight Process Failed Project Plan / (18-07-2017 to 25-07-2017 )

Team	Task’s	Status
Development	-> Requirement gathering	Done	Target 21-07-2017
	-> Understanding Requirement’s	Done
	-> Requirement doc	Review Pending
	-> Detail Design doc	Review Pending
	-> Test Plan doc	Done

Build & Integration	-> Search for a Python library to read an email	Done	Target 22-07-2017
	-> Search for unseen mails	Done
	-> In unseen mails exist read the subject of each mail	Done
	-> Comare the subject with “Build failed in Jenkins”	Done
	-> If subject matches with that string ,generate an alarm and Flash the sreen in raspberry pi	Done
	-> If there is no user interaction with raspberry pi,then generate an alarm for a particular period of time	Pending
	-> If user interaction is present,then user should stop the alarm/Flash message	Pending

Build & Integration	-> Installation of Jenkins and	Done	Target 22-07-2017
	Create the Account	Done
	-> Generate pub key	Done
	-> Create New Project	Done
	-> Source code Management using git repository	Done
	-> Create batch file to run on Build	PartialDone
	-> Email configuration	Partial Done
	-> Install Required plugin	Pending
	-> Alaram Setup	Pending

Testing	-> Analyzing the requirement document.	Done	Target 24-07-2017
	-> Test environment setup.	Done
	-> Writing test cases as per the specifications.	Partial Done
	-> Analyze the test cases for feasibility of automation	Partial Done
	-> Writing scripts for automation testing	Pending
	-> Perform Test execution	Pending
	-> Test Report.	Pending